## app-workflows
S.NO | Workflow Type | Workflow | DB schema work | Backend Work | UI work
1 | Resident | Login | Done - Supabase Auth built-in (auth.users / auth.identities) | Done - Supabase Auth signInWithPassword (mobile calls Supabase directly; backend also has a redundant POST /auth/login used only by test scripts) | Done - LoginScreen.js
2 | Resident | Logout | Done - Supabase Auth built-in | Done - Supabase Auth signOut | Done - Sign out link on DuesScreen.js / AdminReviewScreen.js
3 | Resident | View Billing Periods (All) -- Their Live Receipt view | Done - billing_periods table + resident-view RLS | Partial - GET /me returns only Open periods for the resident's own houses; no endpoint returns Closed/Waived history | Partial - DuesScreen.js shows only open dues to select/pay; no full history/receipt view
4 | Resident | View Transactions ( all ) | Done - transactions table + RLS | Partial - GET /houses/:houseId/transactions exists per-house only; no aggregated "all my transactions" endpoint | Not Built - no screen shows a resident's past transaction history
5 | Resident | Do Transection | Done - transactions + transaction_allocations (FIFO) | Done - POST /transactions | Done - SubmitPaymentScreen.js
1 | Admin | Login | Done - Supabase Auth built-in | Done - Supabase Auth signInWithPassword (shared with Resident login) | Done - LoginScreen.js (shared) + ModeChooserScreen.js after login
2 | Admin | Logout | Done - Supabase Auth built-in | Done - Supabase Auth signOut | Done - Sign out link (shared screens)
3 | Admin + Committee | view society | Done - societies table + RLS | Done - GET /society | Not Built
4 | Admin + Committee | view houses | Done - houses table + RLS | Done - houses list embedded in GET /me for Admin/Committee (no standalone GET /houses list route) | Not Built
5 | Admin + Committee | view members | Done - society_members table + RLS | Done - GET /members | Not Built
6 | Admin | create members | Done | Done - POST /members (creates auth.users + society_members; temp password returned if none supplied) | Not Built
7 | Admin | update members (for admin , committee members etc) | Done | Done - PATCH /members/:id (is_admin / is_committee_member / phone_number) | Not Built
8 | Admin | approve members -- does this make sense? | Partial - status column supports an unused 'Invited' value | Not Built - POST /members creates members directly as Active; no invite/request-then-approve flow exists | Not Built
9 | Admin | suspend member | Done - status column made a real RLS gate | Done - POST /members/:id/suspend and /reactivate | Not Built
10 | Admin | create house-member linkage | Done - resident_house_assignments | Done - POST /assignments (lands as Pending; two-step create-then-approve by design) | Not Built
11 | Admin + Committee | view house-member linkage | Done | Done - GET /assignments (also embedded in GET /members and GET /me) | Not Built
12 | Admin | delete house -member linkage | Done | Done - POST /assignments/:id/revoke (soft-delete via status=Revoked not a hard DB delete) | Not Built
13 | Admin | update linkage | Done | Done - POST /assignments/:id/reassign (revokes old row + creates new Active row) | Not Built
14 | Admin | approve assignment | Done | Done - POST /assignments/:id/approve | Not Built
15 | Admin | create billing record for a house (next month or future months for advance payment) | Done - billing_periods table | Partial - only auto-generated as a side effect of a payment covering more months than are currently Open; no direct admin-triggered create action | Not Built
16 | Admin | create billing record for all house (next month only) | Done - table supports it | Not Built - no bulk monthly-generation job or endpoint exists | Not Built
17 | Admin + Committee | view billing records for a house (all months) | Done | Partial - full data available via GET /me's billingPeriods array for Admin/Committee; no dedicated per-house filtered endpoint | Not Built
18 | Admin + Committee | view billing records for all house for a month (select month) | Done | Partial - same GET /me billingPeriods array covers this; no month-filter endpoint | Not Built
19 | Admin | update billing -- for waived (close is done when transaction is approved) | Partial - 'Waived' is a valid status value in the CHECK constraint | Not Built - nothing ever sets a billing period to Waived | Not Built
20 | Admin + Committee | pay self maintenance | Done | Done - POST /transactions (same endpoint used by any resident) | Done - DuesScreen.js + SubmitPaymentScreen.js when in Resident mode
21 | Admin | pay non maintenance - salary / expenses (auto approved) | Done - transaction_type / payee_name / nullable house_id + CHECK constraints | Done - POST /transactions non-Maintenance branch (Admin-only; auto-Verified at creation) | Not Built - no screen lets an Admin record an expense
22 | Admin + Committee | view transactions -- report | Done | Partial - GET /transactions/pending (Submitted only) + per-house GET /houses/:houseId/transactions; no full all-status society-wide report | Partial - AdminReviewScreen.js shows only the Pending review queue
23 | Admin + Committee | view transaction for a house | Done | Done - GET /houses/:houseId/transactions | Not Built - endpoint exists but no mobile screen calls it
24 | Admin + Committee | view transaction for a billing period | Done - transaction_allocations links transactions to billing periods | Partial - allocation data is embedded in GET /houses/:houseId/transactions; no dedicated by-billing-period endpoint | Not Built
25 | Admin | generate pendency report for a month | Partial - underlying billing_periods data exists | Not Built - no aggregated pendency-report endpoint | Not Built
26 | Admin | transaction approve | Done | Done - POST /transactions/:id/verify | Done - AdminReviewScreen.js Verify button
27 | Admin | transaction reject | Done | Done - POST /transactions/:id/reject | Done - AdminReviewScreen.js Reject flow (inline reason box)
28 | Admin | upload bank statement | Not Built | Not Built | Not Built
29 | Admin | update society settings (name / UPI VPA / payee name / timezone) | Done - societies table + RLS | Done - PATCH /society/:id | Not Built
30 | Admin + Committee | view audit log / activity history | Done - audit_events table + Admin/Committee SELECT RLS | Not Built - written to on every mutation (create/suspend/verify/reject/approve/revoke/reassign) but never read back by any endpoint | Not Built
31 | Admin + Committee | export transaction / billing statement (PDF or CSV) | Done - underlying data exists across transactions / billing_periods | Not Built | Not Built
1 | Automation | Auto Reconcile txn | Not Built | Not Built | N/A
2 | Automation | send dues reminder / notification (upcoming or overdue billing period) | Partial - billing_periods (amount_due / period_month / status) already has everything needed to compute who is due | Not Built - no scheduled job or notification-send endpoint exists | N/A - a push/SMS/email trigger | not a screen
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add a new screen that will display all periods for a house and a button to launch it.
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add New screen that display all txn for a house.
Note on C15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not required
Note on C31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add screen with billing period selector
Note on C32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Intent is to know who didn’t paid this month. Can be given from billing_period table view.
Note on C35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Do we need any DB object for this? I guess NO